## NPV
Market Share | 60% |  | REF PARAM | Analysis ACFT |  | IRR
Interest rate | 5% |  | MTOW (kg) | 50000 |  | 37.22%
|  |  | wS (m2) | 80
|  |  | nEng | 2
|  |  | Tmax | 22000
|  |  | Nacele diam (m) | 1.4
|  |  | NPAX | 114
Year | Deliveries | Accum Deliveries | Sales (Mi USD) | Cost (Mi USD) | Cash Flow (Mi USD) | NPV
1 | 0 | 0 | 0 | 261.6023 | -261.6023 | -261.6023
2 | 0 | 0 | 0 | 309.1993 | -309.1993 | -294.4756
3 | 0 | 0 | 0 | 257.9759 | -257.9759 | -233.9917
4 | 0 | 0 | 0 | 85.992 | -85.992 | -74.2831
5 | 6 | 6 | 313.4939 | 232.1346 | 81.3593 | 66.9345
6 | 20 | 26 | 1044.9796 | 759.2118 | 285.7677 | 223.9065
7 | 44 | 70 | 2298.955 | 1660.6173 | 638.3377 | 476.3374
8 | 92 | 162 | 4806.906 | 3459.7123 | 1347.1936 | 957.4254
9 | 94 | 256 | 4911.4039 | 3526.6955 | 1384.7084 | 937.2251
10 | 102 | 358 | 5329.3957 | 3821.0325 | 1508.3632 | 972.3044
11 | 94 | 452 | 4911.4039 | 3517.8937 | 1393.5102 | 855.4944
12 | 90 | 542 | 4702.408 | 3366.1644 | 1336.2436 | 781.274
13 | 84 | 626 | 4388.9141 | 3140.6085 | 1248.3057 | 695.1033
14 | 30 | 656 | 1567.4693 | 1121.4159 | 446.0535 | 236.5517
|  | TOTAL | 34275.3294 | 25520.256 | 8755.0734 | 5338.2039

## COSTS
NON-RECURRING COSTS
Year | Manpower | Infra | Gen | total | Total Manufacturer
1 | 268605841.847 | 86192723.8891 | 18919035.2567 | 373717600.9929 | 261602320.695
2 | 376048178.5859 | 39178510.8587 | 26486649.3594 | 441713338.8039 | 309199337.1628
3 | 322327010.2164 | 23507106.5152 | 22702842.308 | 368536959.0397 | 257975871.3278
4 | 107442336.7388 | 7835702.1717 | 7567614.1027 | 122845653.0132 | 85991957.1093
TOTAL | 1074423367.3882 | 156714043.4348 | 75676141.0268 | 1306813551.8498 | 914769486.2948
RECURRING COSTS
Year | Deliveries | Material Costs | Manpower Cost | COST OF SALES (17% 1+2) | PROCESSING COST (8% 1+2) | GENERAL COST (5% 1) | TOTAL
5 | 6 | 166535780.5433 | 12510449.7955 | 30437859.1576 | 14323698.4271 | 8326789.0272 | 232134576.9508
6 | 20 | 555119268.4778 | 30045433.8937 | 99477999.4032 | 46813176.1897 | 27755963.4239 | 759211841.3883
7 | 44 | 1221262390.6512 | 58380963.1985 | 217539370.1545 | 102371468.308 | 61063119.5326 | 1660617311.8447
8 | 92 | 2553548634.9979 | 112079282.1445 | 453156745.9142 | 213250233.3714 | 127677431.7499 | 3459712328.1779
9 | 94 | 2609060561.8457 | 107933439.3458 | 461888980.2025 | 217359520.0953 | 130453028.0923 | 3526695529.5816
10 | 102 | 2831108269.2368 | 112473421.1722 | 500408887.3695 | 235486535.2327 | 141555413.4618 | 3821032526.4731
11 | 94 | 2609060561.8457 | 100891980.9178 | 460691932.2698 | 216796203.4211 | 130453028.0923 | 3517893706.5466
12 | 90 | 2498036708.1501 | 94973307.5875 | 440811702.6754 | 207440801.259 | 124901835.4075 | 3366164355.0795
13 | 84 | 2331500927.6068 | 87725806.4516 | 411268544.7899 | 193538138.7247 | 116575046.3803 | 3140608463.9533
14 | 30 | 832678902.7167 | 31146637.8919 | 146850341.9035 | 69106043.2487 | 41633945.1358 | 1121415870.8966
TOTAL | 656 | 18207912006.072 | 748160722.3989 | 3222532363.8401 | 1516485818.2777 | 910395600.3036 | 24605486510.8923

## DATA
REF date | 2015-05-01
REF PARAM | Baseline ACFT | Analysis ACFT
MTOW | 22010 | 50000
wS | 52 | 80
nEng | 2 | 2
Nacele diam | 1.52 | 1.4
NPAX | 50 | 114
Tmax | 8895 | 22000
kVA | 75 | 75
Program Share |  | AVG Man power cost (US$/h)
Manufacturer | 70% | 41.72
Partner | 30% | 83.44
Average |  | 54.236
MANPOWER DISTRIBUTION (PROD DEV COST)
YEAR1 | 25%
YEAR2 | 35%
YEAR3 | 30%
YEAR4 | 10%
INFRA COST DISTRIBUTION
YEAR1 | 55%
YEAR2 | 25%
YEAR3 | 15%
YEAR4 | 5%
GEN COST DISTRIBUTION
YEAR1 | 25%
YEAR2 | 35%
YEAR3 | 30%
YEAR4 | 10%
ITEM | Complexity Factor
Landing Gear | 1.2
Flight Controls | 1.4
Engines | 1.1
Naceles | 1
Interior | 1
Electrical System | 1.3
Avionics | 0.9
Structures | 1.5
Fuel System | 1
Market Share | 60% | 60%
Year | Deliveries (Baseline) | Deliveries (Analysis)
5 | 6 | 6
6 | 20 | 20
7 | 44 | 44
8 | 92 | 92
9 | 94 | 94
10 | 102 | 102
11 | 94 | 94
12 | 90 | 90
13 | 84 | 84
14 | 30 | 30
LC PER HOUR | 25
Sales Price | Baseline | Analysis
| 23000000 | 52248977.7374
Weight adj | 52248977.7374

## MAN POWER
MANAGEMENT AND ADMINISTRATION (Hours) |  |  | ENGINEERING (Hours) |  |  | TESTING AND VALIDATION (Hours) |  |  | SUPPORT (Hours)
ITEM | Baseline ACFT | Analysis ACFT | ITEM | Baseline ACFT | Analysis ACFT | ITEM | Baseline ACFT | Analysis ACFT | ITEM | Baseline ACFT | Analysis ACFT
Preliminary Design | 27983 | 27983 | Aerodynamics | 135050 | 306792.3671 | Ground testing | 208050 | 472626.0791 | Service Bulletins | 19467 | 19467
Interior | 229950 | 522376.1926 | Aeroelasticity | 237250 | 538959.5638 | System testing | 111933 | 254277.6011 | Spare Parts | 103417 | 234931.8492
Structures | 279833 | 635695.1386 | Performance | 76650 | 174125.3975 | Flight Test | 160600 | 364834.1663 | Operations Manuals | 203183 | 203183
Electrics/Avionics | 365000 | 829168.5597 | Structures | 365000 | 829168.5597 | Instrumentation | 122883 | 279152.6579 | Customer Services | 6083 | 6083
Mechanics | 121667 | 276390.2771 | Interior | 92467 | 210056.7924 | Pilots | 48667 | 110556.5652 | Documentation | 128967 | 128967
Hydraulics | 60833 | 138194.0027 | Electrics/Avionics | 365000 | 829168.5597 | Prototypes | 2828750 | 6426056.338 | Technical Support | 77867 | 77867
Propulsion | 51100 | 126385.6099 | Mechanics | 399067 | 906558.3826 | Rigs | 60833 | 138194.0027 | Maintenace Plan | 96117 | 96117
TOTAL |  | 2556192.7807 | Hydraulics | 97333 | 221110.8587 | Body of proof | 97333 | 221110.8587 | TOTAL |  | 766615.8492
|  |  | Propulsion | 121667 | 300918.9432 | Prot Maintenance | 585217 | 1329434.348
|  |  | Certification | 121667 | 276390.2771 | Manufacturing Tooling | 526817 | 1196767.3785
|  |  | Configuration Ctrl | 62050 | 62050 | Methods and Process | 784750 | 784750
|  |  | Technical Docs | 115583 | 115583 | Quality Control | 138700 | 138700
|  |  | TOTAL |  | 4770882.702 | TOTAL |  | 11716459.9955
GRAND TOTAL | 19810151.3273 | Hours
| 1074423367.3882 | USD
MAN POWER COSTS OVERTIME
Y1 | 268605841.847
Y2 | 376048178.5859
Y3 | 322327010.2164
Y4 | 107442336.7388

## INFRA COST
INFRASTRUCTURE COSTS (US$)
ITEM | Baseline ACFT | Analysis ACFT
Machines&Equip | 17880000 | 40617900.9541
FSW | 9536000 | 21662880.5089
Prototypes | 35760000 | 81235801.9082
Assembly Line | 1192000 | 2707860.0636
Computer Resources | 6913600 | 6913600
Instruments | 596000 | 596000
Offcie Supplies | 596000 | 596000
Software | 1788000 | 1788000
Other Investments | 596000 | 596000
TOTAL |  | 156714043.4348
INFRASTUCTURE COSTS OVERTIME
Y1 | 86192723.8891
Y2 | 39178510.8587
Y3 | 23507106.5152
Y4 | 7835702.1717

## GEN COST
GENERAL COSTS (US$)
ITEM | Baseline ACFT | Analysis ACFT
Communications | 834400 | 834400
Instrumentation and FT | 4529600 | 4529600
Tooling | 2980000 | 2980000
Travel | 5006400 | 5006400
Third part man-power | 23840000 | 23840000
Third part man-powerm (partners) | 27416000 | 27416000
Fuel | 4872900 | 11069741.0268
TOTAL |  | 75676141.0268
INFRASTUCTURE COSTS OVERTIME
Y1 | 18919035.2567
Y2 | 26486649.3594
Y3 | 22702842.308
Y4 | 7567614.1027

## MATERIAL
Material COSTS (US$)
ITEM | Cost Parameter |  | Baseline ACFT | Analysis ACFT | Complexity Factor | MATERIAL COST Baseline ACFT | MATERIAL COST Analysis ACFT
Landing Gear | 8 | USD/kg MTOW | 22010 | 50000 | 1.2 | 211296 | 480000
Flight Controls | 834 | wS USD/ft2 | 559.4368 | 860.672 | 1.4 | 653198.4077 | 1004920.6272
Engines | 2000000 | unit | 2 | 2 | 1.1 | 4400000 | 10882518.2687
Naceles | 11920 | diameter in | 59.8424 | 55.118 | 1 | 713321.408 | 657006.56
Interior | 19072 | per PAX | 50 | 114 | 1 | 953600 | 2174208
Electrical System | 8940 | per KVA | 75 | 75 | 1.3 | 871650 | 871650
Avionics | 953600 | per assaembly | 1 | 1 | 0.9 | 858240 | 858240
Structures | 143 | USD/kg MTOW | 22010 | 50000 | 1.5 | 4721145 | 10725000
Fuel System | 119 | USD/ft2 | 559.4368 | 860.672 | 1 | 66572.9792 | 102419.968
TOTAL | [6 empty] | 27755963.4239

## MAN POWER RC
MANPOWER RC COST
Year | Deliveries | WH Per unit (Baseline) | Cost Per unit (Baseline) | Total Manpower Cost (Baseline) | Total Manpower Cost (analysis)
5 | 6 | 36714 | 917850 | 5507100 | 12510449.7955
6 | 20 | 26452 | 661300 | 13226000 | 30045433.8937
7 | 44 | 23363 | 584075 | 25699300 | 58380963.1985
8 | 92 | 21451 | 536275 | 49337300 | 112079282.1445
9 | 94 | 20218 | 505450 | 47512300 | 107933439.3458
10 | 102 | 19416 | 485400 | 49510800 | 112473421.1722
11 | 94 | 18899 | 472475 | 44412650 | 100891980.9178
12 | 90 | 18581 | 464525 | 41807250 | 94973307.5875
13 | 84 | 18389 | 459725 | 38616900 | 87725806.4516
14 | 30 | 18281 | 457025 | 13710750 | 31146637.8919